## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES (ACCEPTANCE CRITERIA)
9 | As a customer, I want to access the home page, so that I can access the read about us page |  | High | Medium | Done |  | DoD The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. General users are able to create a new account and will allow them to sell their personal books
11 | As an administrator, I want to accept or deny registrations, so that businesses can be properly approved. |  | High | Large | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin users are given access to a list of users connected and registered to a business and are able to accept or reject the users based on the legitimacy of the brand. | Given that I am a verified administrator with appropriate credentials and access to business approvals When I access the admin homepage and select pending approvals Then I will be directed to the business approvals page where I can accept or reject business wanting to be integrated into the webpage.
21 | As a user, I want to view the cover image of the book I'm looking for so that I can get a first impression of what the book might be about. |  | High | Small | Done | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. | Given that the user is on the book products list And finds the book they are looking for When they click on the book product and the page has loaded up Then the cover image is viewable and the user can get a first impression of the book
22 | As a user, I want to view the table of contents of the book I'm looking for so that I can acquire an idea of how long the book might be. |  | High | Small | Done | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. | Given that the user is on the book products list And finds the book they are looking for When they click on the book product and then click on ‘Tables of Contents’ Then the user can view the tables of contents and see how long the book is.
23 | As a user, I want to view the table of contents of the book I own so that I can skip to the chapters that sound interesting. |  | High | Small | Done | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. | Given that the user is on the book products list And finds the book they own When they click on the book product and then click on ‘Tables of Contents’ Then the user can view the tables of contents and skip to the chapters they want.
27 | As an administrator, I want to login to an administrator account, so that I can add new users |  | High | Large | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin users are able to access all users profiles are able to accept or reject them within the system | Acceptance Criteria Given that I am a public user is a verified individual with a verified user account When I access the homepage and select the share books button Then I will be directed a sharing page where I can post my findings regarding a particular book
31 | As a user, I want to view all the available books in the website so I can browse through many different types of books |  | High | Large | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that a customer is on the website When I access the homepage and select VIEW BOOKS button Then I will be directed a separate page listing all the available products within BOOKEROO
32 | As a customer, I want to access the sign up page, so that I can register an account to use the site |  | High | Small | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that a customer is on the website When I access the homepage and select SIGN UP icon Then I will be directed a separate page allowing me to register on the website
33 | As a customer, I want to access the login page, so that I can log in to my registered account and make use of the site |  | High | Small | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that a customer is on the website When I access the homepage and select SIGN UP icon Then I will be directed a separate page allowing me to register on the website
34 | As a user, I want a landing page for when I first access the site, so that I have multiple options presented to me depending on what I want to do |  | High | Medium | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that a customer first accesses the website When I enter into the landing page Then the page displays options for navigating into different activities.
2 | As a customer, I want to search for a book by its name, so that I can see if a book is available for purchase. |  | Medium | Medium | Done | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the homepage When the customer clicks on the search bar And the customer types the name of a book And the customer clicks the search button Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page Criterion 2: Given the customer is on the homepage When the customer clicks on the search bar And the customer types the name of a book And the customer presses enter Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page
3 | As a customer, I want to search for books written by an author, so that I can see what books by that author are available for purchase. |  | Medium | Medium | Done | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the homepage When the customer clicks on the search bar And the customer types an author’s name And the customer clicks the search button Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page Criterion 2: Given the customer is on the homepage When the customer clicks on the search bar And the customer types an author’s name And the customer presses enter Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page
4 | As a customer, I want to search for a book by its ISBN, so that I can see if a book is available for purchase. |  | Medium | Medium | Done | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the homepage When the customer clicks on the search bar And the customer types the ISBN of a book And the customer clicks the search button Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page Criterion 2: Given the customer is on the homepage When the customer clicks on the search bar And the customer types the ISBN of a book And the customer presses enter Then a list of search results is shown And the books most relevant to what the user entered are at the top of the list And each item in the list has a link to that book’s page
30 | As a customer, I want to access the about us page, so that I can view general information about the website |  | Medium | Small | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that a customer is on the website When I access the homepage and select ABOUT US icon Then I will be directed a separate page explaining about the organization of BOOKEROO
5 | As a customer, I want to search for a category of books, so that I can see what books in that category are available for purchase. |  |  |  | To Do | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the homepage When the customer clicks on the search bar And the customer types a book category And the customer clicks the search button Then a list of search results is shown And books in the category the user searched for are at the top of the list And each item in the list has a link to that book’s page Criterion 2: Given the customer is on the homepage When the customer clicks on the search bar And the customer types a book category And the customer presses enter Then a list of search results is shown And books in the category the user searched for are at the top of the list And each item in the list has a link to that book’s page
6 | As a customer, I want to leave a review on a book I have purchased, so that I can inform others on whether or not the book is good. |  |  |  | To Do | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the page of the book they wish to review And the customer is logged in And the customer previously purchased the book using this account When the customer enters a review into the review text field And the review is not empty And the customer clicks the ‘Leave Review’ button Then a review is placed And the review is saved to the database Criterion 2: Given the customer is on the page of the book they wish to review And the customer is logged in And the customer previously purchased the book using this account When the customer clicks the ‘Leave Review’ button And they have not yet typed anything into the review Then the user is prompted to enter a review And the review is not saved to the database
7 | As a customer, I want to leave a review on a user I have purchased a book from, so that I can inform others on whether or not the seller is good |  |  |  | To Do | Acceptance criteria met // Unit tests have been written and pass // Code has been merged into the development branch // Tested under production environment | Criterion 1: Given the customer is on the page of the user they wish to review And the customer is logged in And the customer has previously purchased a book from this seller using this account When the customer enters a review into the review text field And the review is not empty And the customer clicks the ‘Leave Review’ button Then a review is placed And the review is saved to the database Criterion 2: Given the customer is on the page of the user they wish to review And the customer is logged in And the customer has previously purchased a book from this seller using this account When the customer clicks the ‘Leave Review’ button And they have not yet typed anything into the review Then the user is prompted to enter a review And the review is not saved to the database
8 | As a shop owner, I want to sign up and create an account, so that I can sell my own books |  |  |  | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. The Shop Owner can sell particular books based on the genre | Given that the shop owner has a business orientated account When I select option to sell button Then the website verifies my account and provides me with my product offering page
10 | As a public user, I want to be able to sign into my account, so that I can share my books to other public users |  |  |  | To Do | DoD The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. General users are able to connect with other general users and are able to share specific books to them | Acceptance Criteria Given that I am a public user is a verified individual with a verified user account When I access the homepage and select the share books button Then I will be directed a sharing page where I can post my findings regarding a particular book
12 | As a customer, I want to pay for books using PayPal, so that I can make transactions easily and securely. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that the customer has a PayPal account When I click on the confirm purchase button Then the website verifies my account and makes the transaction.
13 | As a buyer, I want to pay for books using PayPal, so that I can make transactions easily and securely. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that the buyer has a PayPal account When the click on the confirm purchase button Then the website verifies my account and makes the transaction.
14 | As a customer, I want to be able to receive payments for books, so that I can make a profit from the online store. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that a customer purchases my product When the transaction is complete on the website and the refund period is over Then the website validates the transaction and gives me my share of the profit.
15 | As a buyer, I want to be able to receive payments for books, so that I can make a profit from the online store. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that a buyer purchases my product When the transaction is complete on the website and the refund period is over Then the website validates the transaction and gives me my share of the profit.
16 | As a customer, I want to be able to cancel my order within 2 hours of purchase, so that I can receive a refund in case I change my mind. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that the customer purchased a book and the refund period isn’t over When I click on the cancel order button Then the website cancels the order and refunds my payment.
17 | As a buyer, I want to be able to cancel my order within 2 hours of purchase, so that I can receive a refund in case I change my mind. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that the customer purchased a book and the refund period isn’t over When I click on the cancel order button Then the website cancels the order and refunds my payment.
18 | As a customer, I want to see a history of my transactions, so that I can keep track of my purchases. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that I have multiple purchases as a customer When I click on ‘purchase history’ button Then the website shows me a list of my purchases and total spendings.
19 | As a shop owner, I want to be able to see the status of current orders, so that I know whether to hold the product depending on if it’s cancelled. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that I have multiple sales as a shop owner When I click on ‘sales history’ button Then the website shows me a list of my sales and total earnings.
20 | As a shop owner, I want to be able to see the status of current orders, so that I know whether to hold the product depending on if it’s cancelled. |  |  |  | To Do | - The story is fully implemented and feature complete. - Unit testing is completed with at least 90% coverage. - Acceptance testing is completed with at least 90% coverage. - Product Owner signs off on the user story. -Features are deployed into production. -The customer can receive payments for books using PayPal. - Payment features are completed and reviewed by at least one other developer. | Given that I am a shop owner with multiple sales requests When I click on ‘order status’ button Then the website shows me a list of my orders and their status.
24 | As an admin, I want to download a report on recent user transactions in csv format so that I can see how our sales are going. |  |  |  | To Do | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. - The admin can download reports on both recent user transactions and books | Given that the user is a logged in admin And is on the Admin Features page When the admin clicks on ‘Download Recent User Transactions Report’ Then the admin should be able to download the report in csv format and identify how the sales are going.
25 | As an admin, I want to download a report about books in csv format so that i can see what books we have in stock. |  |  |  | To Do | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. - The admin can download reports on both recent user transactions and books | Given that the user is a logged in admin And is on the Admin Features page When the admin clicks on ‘Download Books Report’ Then the admin should be able to download the report in csv format and identify how many books and what books are in stock.
26 | As an admin, I want to download a report on recent user transactions in csv format so that I can identify any suspicious purchases. |  |  |  | To Do | - The story is fully implemented and feature complete - Unit Testing is completed with at least 90% coverage - Acceptance Testing is completed with at least 90% coverage - Product Owner signs off on the user story. - Features are deployed into production. - The admin can download reports on both recent user transactions and books | Given that the user is a logged in admin And is on the Admin Features page When the admin clicks on ‘Download Recent User Transactions Report’ Then the admin should be able to download the report in csv format and observe for any suspicious transactions.
28 | As a public user, I want to create an account, so that I can purchase books suited to my taste. |  |  |  | Done | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Public users are able to access their account and purchase books available | Acceptance Criteria Given that I am a public user is a verified individual with a verified user account When I access the homepage and select the share books button and put in my specific filter for genre options Then I will be directed a selling page of books accustomed to my filtering options
29 | As an administrator, I want to be able to access past and current transactions, so that I can view transactions in order. |  |  |  | To Do | The story is fully implemented and feature complete. Unit testing is completed with at least 90% coverage. Acceptance testing is completed with at least 90% coverage. Product Owner signs off on the user story. Features are deployed into production. Admin user is able to visually see a view of all transactions in an orderly format so that transactions are able to be viewed more effectively | Given that I am an admin user, with proper access to transactions history When I access the admin homepage and view the transactions history page Then I will be able to view all transactions made in a orderly manner

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a customer, I want to access the home page, so that I can access the read about us page | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As an administrator, I want to accept or deny registrations, so that businesses can be properly approved. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a user, I want to view the cover image of the book I'm looking for so that I can get a first impression of what the book might be about. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a user, I want to view the table of contents of the book I'm looking for so that I can acquire an idea of how long the book might be. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a user, I want to view the table of contents of the book I own so that I can skip to the chapters that sound interesting. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As an administrator, I want to login to an administrator account, so that I can add new users | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a user, I want to view all the available books in the website so I can browse through many different types of books | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a customer, I want to access the sign up page, so that I can register an account to use the site | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a customer, I want to access the login page, so that I can log in to my registered account and make use of the site | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As a user, I want a landing page for when I first access the site, so that I have multiple options presented to me depending on what I want to do | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a customer, I want to search for a book by its name, so that I can see if a book is available for purchase. | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As a customer, I want to search for books written by an author, so that I can see what books by that author are available for purchase. | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a customer, I want to search for a book by its ISBN, so that I can see if a book is available for purchase. | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As a customer, I want to access the about us page, so that I can view general information about the website | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As a customer, I want to search for a category of books, so that I can see what books in that category are available for purchase. | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As a customer, I want to leave a review on a book I have purchased, so that I can inform others on whether or not the book is good. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a customer, I want to leave a review on a user I have purchased a book from, so that I can inform others on whether or not the seller is good | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a shop owner, I want to sign up and create an account, so that I can sell my own books | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a public user, I want to be able to sign into my account, so that I can share my books to other public users | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a customer, I want to pay for books using PayPal, so that I can make transactions easily and securely. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As a buyer, I want to pay for books using PayPal, so that I can make transactions easily and securely. | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a customer, I want to be able to receive payments for books, so that I can make a profit from the online store. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a buyer, I want to be able to receive payments for books, so that I can make a profit from the online store. | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a customer, I want to be able to cancel my order within 2 hours of purchase, so that I can receive a refund in case I change my mind. | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As a buyer, I want to be able to cancel my order within 2 hours of purchase, so that I can receive a refund in case I change my mind. | #N/A | #N/A | #N/A | #N/A | #N/A