## Product Backlog
SPRINT #3 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
22 | As a user, I want to view the table of contents of the book I'm looking for so that I can acquire an idea of how long the book might be. | 22.1 | Create a basic page design for book products | Mohammed |  |  | X
|  | 22.2 | Create section listing the table of contents | Mohammed |  |  | X
23 | As a user, I want to view the table of contents of the book I own so that I can skip to the chapters that sound interesting. | 23.1 | Create a basic page design for book products | Mohammed |  |  | X
|  | 23.2 | Create section listing the table of contents | Mohammed |  |  | X
27 | As an administrator, I want to login to an administrator account, so that I can add new users | 27.1 | Administrator can view a list of users | Rylan |  |  | X
|  | 27.2 | Can add new users as an administrator | Rylan |  |  | X
2 | As a customer, I want to search for a book by its name, so that I can see if a book is available for purchase. | 2.1 | The search bar is created and is displayed on the all books page | Justin |  |  | X
|  | 2.2 | The search filters the books displayed according to the book name searched for. | Justin |  |  | X
3 | As a customer, I want to search for books written by an author, so that I can see what books by that author are available for purchase. | 3.1 | The search bar is created and is displayed on the all books page | Justin |  |  | X
|  | 3.2 | The search filters the books displayed according to the author searched for. | Justin |  |  | X
4 | As a customer, I want to search for a book by its ISBN, so that I can see if a book is available for purchase. | 4.1 | The search bar is created and is displayed on the all books page | Justin |  |  | X
|  | 4.2 | The search filters the books displayed according to the IBSN searched for. | Justin |  |  | X
28 | As a user, I want to create an account, so that I can purchase books suited to my taste. | 28.1 | Create a sign up page | Rylan |  |  | X
|  | 28.2 | Saves account details (username + password) | Daniel |  |  | X

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | As a user, I want to view the table of contents of the book I'm looking for so that I can acquire an idea of how long the book might be. | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a user, I want to view the table of contents of the book I own so that I can skip to the chapters that sound interesting. | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As an administrator, I want to login to an administrator account, so that I can add new users | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | As a customer, I want to search for a book by its name, so that I can see if a book is available for purchase. | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a user, I want to create an account, so that I can purchase books suited to my taste. | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A